## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Inroduction of Project | MUST HAVE | No Dependency | Sushma Nallamaddi | 3- Completed
S1 | S1 | US-001 | Code Requirements, Coding Basics and Resources | MUST HAVE | No Dependency | Sushma Nallamaddi | 3- Completed
S2 | S2 | US-002 | Workflow of Code (libraries, packages, alternatives) | MUST HAVE | VS Code | Sushma Nallamaddi | 3- Completed
S2 | S2 | US-002 | Project Discussion Milestone 1 (Chats/calls ingested; transcription working) | MUST HAVE | VS Code | Sushma Nallamaddi | 3- Completed
S3 | S3 | US-003 | Concepts on NLP and LLM | SHOULD HAVE | GeeksforGeeks, Medium | Sushma Nallamaddi | 3- Completed
S3 | S3 | US-003 | Project Discussion Milestone 2 (LLM scoring functional; quality scores generated) | MUST HAVE | VS Code | Sushma Nallamaddi | 3- Completed
S4 | S4 | US-004 | Concepts on RAG | SHOULD HAVE | ChatGPT | Sushma Nallamaddi | 3- Completed
S4 | S4 | US-004 | Project Discussion Milestone 3 (RAG-powered audits and dashboards operational) | MUST HAVE | VS Code | Sushma Nallamaddi | 3- Completed
S5 | S5 | US-005 | Updates, Reporting code, Bugs and error fixing | SHOULD HAVE | No Dependency | Sushma Nallamaddi | 3- Completed
S5 | S5 | US-005 | Project Discussion Milestone 4 (Alerts/reporting deployed; system live) | MUST HAVE | Github | Sushma Nallamaddi | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 60 | 23 | 14 | 7 | 9 | 4 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1- 5 BACKLOG
US-001 | 1 | Inroduction of Project | 2025-12-08 | 2025-12-09 | Sushma Nallamaddi | Others | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Code Requirements, Coding Basics and Resources | 2025-12-10 | 2025-12-12 | Sushma Nallamaddi | Others | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 3 | Workflow of Code (libraries, packages, alternatives) | 2025-12-15 | 2025-12-15 | Sushma Nallamaddi | Design | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 4 | Project Discussion Milestone 1 (Chats/calls ingested; transcription working) | 2025-12-16 | 2025-12-19 | Sushma Nallamaddi | Coding | 3- Completed | 11 | 3 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 5 | Concepts on NLP and LLM | 2025-12-22 | 2025-12-22 | Sushma Nallamaddi | Others | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 6 | Project Discussion Milestone 2 (LLM scoring functional; quality scores generated) | 2025-12-23 | 2025-12-27 | Sushma Nallamaddi | Coding | 3- Completed | 12 | 4 | 3 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 7 | Concepts on RAG | 2025-12-29 | 2025-12-31 | Sushma Nallamaddi | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 8 | Project Discussion Milestone 3 (RAG-powered audits and dashboards operational) | 2026-01-02 | 2026-01-09 | Sushma Nallamaddi | Coding | 3- Completed | 12 | 4 | 0 | 0 | 3 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 9 | Updates, Reporting code, Bugs and error fixing | 2026-01-12 | 2026-01-13 | Sushma Nallamaddi | Others | 2- In Progress | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 10 | Project Discussion Milestone 4 (Alerts/reporting deployed; system live) | 2026-01-19 | 2026-01-23 | Sushma Nallamaddi | Coding | 3- Completed | 8 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Dec 8-12 | Inconsistent chat and call data formats | Defined a unified schema and normalized all transcripts.
Sprint 2 | Dec 15-19 | Low transcription accuracy for noisy audio | Applied audio preprocessing and validated Whisper outputs.
Sprint 3 | Dec 22-27 | Difficulty quantifying empathy and quality metrics | Created fixed scoring rubrics and prompt templates.
Sprint 3 | Dec 29 - Jan 02 | LLM score variability across runs | Controlled temperature and normalized scoring outputs.
Sprint 4 | Jan 05 - 09 | Irrelevant document retrieval in RAG | Improved chunking, embeddings, and metadata filtering.
Sprint 4 | Jan 12-16 | Slow dashboard performance with large data | Optimized queries and added caching.
Sprint 4 | Jan 19-23 | False-positive compliance alerts | Tuned alert thresholds and tested with historical data.
Sprint 5 | Jan 26-28 | Deployment configuration issues | Standardized environments and resolved dependency conflicts.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-08 | 2025-12-12 | Sushma Nallamaddi | Transcript normalization | Manual transcript fixes | Whisper/OpenAI STT | Unified transcript schema
2 | Sprint 2 | 2025-12-15 | 2025-12-19 | Sushma Nallamaddi | Audio preprocessing | Raw noisy audio | Chat & call ingestion | Improved STT accuracy
3 | Sprint 3 | 2025-12-22 | 2026-01-02 | Sushma Nallamaddi | Prompt-based scoring | Subjective scoring | LLM quality evaluation | Defined scoring rubrics
4 | Sprint 4 | 2026-01-05 | 2026-01-23 | Sushma Nallamaddi | Contextual retrieval | Full-document search | RAG audits | Metadata-based chunking
5 | Sprint 5 | 2026-01-26 | 2026-01-28 | Sushma Nallamaddi | Alert tuning & rules | Single-signal alerts | Compliance monitoring | Optimized alert thresholds